## Task
Note: |  | Motor Protection Relay(NGB-Project)
Date | % Complete | Task Name | Duration | Start | Finish | Discriptions
SAT 02/04/22 | 20% | Motor Protection Relay(NGB-Project)
SUN 01/05/22 | 90% | Create Work environment | 1 hrs | 12:00pm | 1:00pm | configure harware initialization using cubmax
SUN 01/05/22 | 90% | Create source code | 1 hrs | 1:00pm | 2:00pm | add rms.c,rms.h,and intialised varibale
MON 02/05/22 | 100% | Add functionality (in main) | 1 hrs | 12:00am | 1:00am | implement call back function,hardware init and helper functions
MON 02/05/22 | 100% | Add functionality(related to adc sample) | 1 hrs | 1:00am | 2:00am | impelment adc sample,stored
MON 02/05/22 | 50% | Add functionality(Add rms calculations) | 1 hrs | 2:00am | 3:00am | impelment rms calculation,eeprom,scalling,and helper function and more
MON 02/05/22 | 100% | Add functionality(Add rms calculations) | 1 hrs | 10:00am | 11:00am | complete impelment rms calculation,eeprom,scalling,and helper function,select adc channel and more
MON 02/05/22 | 20% | Prepare code testing document | 30 min | 11:00am | 11:30am | Prepare code testing document for testing code enginner